## Goal Setting Example
Focus Area | SMART Goal | Milestone | Due Date | Responsible Party | Check-in Plan/Reporting Progress
Overall score | Raise the overall institutional score from 66% to 75% by the end of the academic year. | 1. Create Ally communication plan to help boost faculty engagement. 2. Launch plan. 3. Offer Ally trainings and resources as part of the overarching plan. | 1. July 15th 2. August 18th (or 1 week before fall semester begins) 3. Monthly cadence | Ally administrator and academic administrators (deans, department chairs, etc.). | Review Ally institutional report in monthly intervals and report our progress, or at mid-semester and end of semester.
Accessibility Issues by Severity | Reduce the top 3 severe issues by 50% by end of semester . | 1. Identify top 3 severe issues in the Institutional Report and share out to departments/units involved. 2. Create progress dashboard 3. Create targeted training and support materials focused on each individual issue 4. Host office hours for faculty that have these issues in their courses. | 1. August 25th 2. September 15th 3. September 25th and every month after | Ally administrator and internal champions. | Track monthly changes to the top 3 severe issues and share out progress (use progress dashboard) .
Course-level | Improve accessibility scores in ALL general education courses to at least 75% by end of semester. | 1. Identify all general education courses 2. Work with instructors and departments to use Ally for remediating content and addressing issues 3. Offer trainings and support resources | 1. September 10th 2. September 20th 3. Ongoing | Ally administrators and department chairs and/or deans. | Track monthly improvements and share out progress.
Directory | Increase accessibility scores in departments that have an overall scores of 60% or less by end of semester. | 1. Identify all departments that have an overall score of less than 60%. 2. Create communication plan for department heads/deans, include support and resources. 3. Lead targeted trainings for departments meeting this criteria. | 1. August 15th 2. September 15th 3. October 15th 4. November 15th 5. December 15th | Ally administrators, instructional designers, and department heads and deans. | Track monthly or each semester and share with individual department heads and/or deans.
Qualitative Data | By the end of the next academic year, increase positive faculty sentiment about Ally and digital accessibility by 25%, as measured through qualitative feedback, implementing targeted outreach, showcasing success stories, and offering at least 3 interactive training opportunities tailored to faculty needs. | 1. Analyze existing faculty feedback to identify concerns and establish a baseline for sentiment 2. Develop faculty-centered outreach plan with clear messaging and a schedule of engagement activities. 3. Identify 3-5 accessibility champions among faculty. 4. Launch initial outreach and training, including at least 1 interactive session and informal feedback collection. 5. Mid-year check-in using short survey or focus group to assess progress and adjust strategy if needed. 6. Continue targeted outreach with success stories of identified faculty champions, follow-up resources, and additional training. 7. Collect final feedback, compare to baseline, report on progress toward 25% improvement goal. | 1. Months 1-2 of new academic year 2. Months 2-3 3. Months 3-5 4. Months 6-7 5. Months 7-9 6. Months 9-10 | Ally administrators , instructional designers, department heads and/or deans. | Track overall score on a monthly basis and share out progress with all involved, including identified accessibility champions. Check-in with identified faculty accessibility champions to discuss their progress with colleagues and offer additional resources if needed.